###### CAITHNESS COMMUNITY PLAN – FROM Community Plan for Highland 2004/07

###### PRIORITY AREA 1: DEVELOPING A STRONG, SUSTAINABLE AND COMPETITIVE ECONOMY

###### AIM 1 = More people choosing to live, work and learn in Highland – and able to do so

| What are we going to do | What progress has been made? | Any changes required? |
| --- | --- | --- |
| a) Build centres of excellence within the regional science base and support commercialisation of R & D. | UHI ARC funding – research staff into ERI 5 investigators + post graduates and PHD Students ERI full to capacity New research theme Renewable Energy –(has link to University of British Columbia) DERC PHD students not yet commercialisation Responding to training needs – decommissioning Request to be involved in Energy Institute Nuclear Archive (HC area archives may be relocated there) NHC/HC working with NDA to develop -> Nat Nuclear Skills Academy – project manager post advertised. NDA progressing with Partners Marine Energy (including community) in Pentland Firth Wick District Heating Scheme Watersports – changing rooms, showers, etc in Thurso Drama at NHC Change in emphasis to touring drama to facilities across area to be reviewed – lack of student interest. | Develop HND in Archaeological Practice. Develop positive relationship with Orkney re Archaeology Availability of grid connection Honours year module in Fine Arts at Northlands proposal Water sport capital of Scotland –proposal. |
| b) Strengthen the perception of Caithness as a quality tourist destination and make the whole tourism sector more professional. | North Highland Initiative taking tour operators together – quality product Castle of Mey – cruise ships Country Music Festival ongoing Caithness Walking Festival ongoing Caithness Arts Festival gone beyond pilot Caithness Arts Co-ordinator appointed Arts Development more positive than ever and understanding that evolution must be on economic basis Highlands 2007 has created opportunities River of Stone Greenbadge guides training achieved | Develop getting cruise passengers into towns. Pilot Viewfirth as possible local Arts venue. Research on how to market things better John O’Groats – change of emphasis in what offered – quality of experience |
| c) Develop marketing programmes which reinforce an image of excellence across all sectors | Mey Selections – progress Two Best Awards – Forss and Captain’s Galley Tesco – Caithness Beef/Lamb (Tom Pottinger) Mey selections benefiting islands too. Plans approved – slaughter house in Keiss Increase set up diversification re crafting – food etc Training “Initiative at the Edge” re agriculture etc. Horticulture on a wider sphere – organic education side (HIE based) North Highland Initiative progressing Caithness Horizons developing building work start Traders assisted with marketing in response to Tesco threat | Continue to progress appointment of marketing and development officer Clarify ‘Flag up’ excellence and make it broader Post to market arts in Caithness Help traders to improve shop frontages, windows and customer service and market Potential development of Wick Town Centre as THC moves |
| d) Promote and support inward migration |  | Investment needed Immigration NHC work with Adult Basic Education to share/co-ordinate effort. Develop products re culture (history) housing etc Information Packs – Polish translation Socio-Economic redevelopment of Caithness – post decommissioning Need to continue to develop Partnership and Trust! |
| e) To develop, using a partnership approach, the provision or enabling of childcare to assist the take-up of employment opportunities. | Update to come from Niall Smith CVG |  |
| f) Develop and enhance the social economy in order to strengthen communities and improve confidence and sustainability | Strong track record for developing social economy organisations – in particular PPP, OCA & Home Aid etc | Sustainability? |

PRIORITY AREA 1: DEVELOPING A STRONG, SUSTAINABLE AND COMPETITIVE ECONOMY

AIM 2 = Individuals and communities feel they are dealt with equitably

| What are we going to do | What progress has been made? | Any changes required? |
| --- | --- | --- |
| Commit to the greater dispersal of public sector jobs throughout Highland. | Dental school opened in November 2006 Passport Agency to open shortly Model of advanced build successful | Extension of existing dental facility into Thurso to serve West of County and North Sutherland. Retention and recruitment Continue advance building UHI – Development and co-ordination Jobs dispersal to be developed - THC |
| b) Use reform of the Common Agricultural Policy as an opportunity to develop more employment opportunities from the natural environment. | North Highland Initiative a great success Mey Selections Planning permission granted for Caithness Slaughterhouse Need to diversity accepted by farmers | (Delete ethanol from Caithness Focus) Re Transportation for waste - (Wick Harbour?) Ensure SAC and CASE to meet to address the problem and advise how to move forward?? ERI involvement. |
| c) Identify and develop import substitution programmes, based on better local use of local products. |  |  |

PRIORITY AREA 1: DEVELOPING A STRONG, SUSTAINABLE AND COMPETITIVE ECONOMY

AIM 3 = Highland having the infrastructure to keep it at the forefront of modern and rural regions

| What are we going to do | What progress has been made? | Any changes needed? |
| --- | --- | --- |
| a) Encourage effective business use of modern communications technology. | Broadband good Mobiles Moving businesses to e-commerce e.g. Ackergill Tower. | Consistent Broadband service. Western Isles examples of home working Need to continue to improve Understanding of technology - who is this directed at - how new technology should be understood by businesses Raise awareness within businesses |
| b) Ensure Caithness makes the best possible use of renewable energy. | Conference held on marine. PURE project seminar Energy Institute LD Submission as part of Scottish submission Caithness Heat and Power Scheme – up and running PPP is offering fuel at good price Awaiting info – Pentland Housing survey on fuel poverty Pentland Housing – extra funding for Ormlie Renewables Project Focus on reducing consumption Caithness Heat and Power success story – 3-5 years £200K profit. Re-invest LD Evaluation to be taken | Need to take advantage of ERI Additional funding. Add Partners - Health Board - Highland Council - PPP - Distillery |
| c) Improve freight and business transport. | Bad weather shows how vulnerable area is with train, sea and road links. | Link to priority 5 Add member Wick Airport - HIE Push for better air connection times Push for GPS for Wick. |

###### Priority Area 2 - Encouraging Lifelong Learning and Developing Community Capacity

###### AIM 1- More people choosing to live, work and learn in highland – and able to do so

| What are we going to do | What Progress Has Been Made? | Any Changes Needed? |
| --- | --- | --- |
| a) Implementation of the Highland Community Learning Strategy. | CLD Strategy Ongoing reviews | Review minutes available on web. |
| b) Support Adult Literacy and Numeracy learners. | Adult literacy & numeracy | Add in NHS as partners. Need more info on incomers re language demands Job Centre as central info point Establish to 1d) re migrant workers strategy |
| c) Build on existing initiatives to encourage high standards of continuing professional development in all sectors. | Who did audit?/but think it is a good idea. | Add in PPP, clarification of outputs |
| d) Promoting the role of cultural and sporting activity as pathways to lifelong learning | Halkirk development High School development Viewfirth development ASC initiative in place | Add youth organisations |
| e) | Highland welcome package | Add NHC Change to Fresh Talent Create a welcome ‘cultural’ package |
| f) | Complete | Conference?? |

###### Priority Area 2 - Encouraging Lifelong Learning and Developing Community Capacity

###### AIM 2 + Individuals and Communities feel they are dealt with equitably

| What are we going to do | What Progress Has Been Made? | Any Changes Needed? |
| --- | --- | --- |
| a) Target training programmes towards known skills gaps. Employability Interventions to help economically inactive back into work | Increase in programmes Tesco initiative Functioning Partnership – examples given | Add CASE, CRF Group |
| b) Promote attainment and achievement for all |  | Include high schools Attainment agenda Add CASE Clarification on what socio-economic base line is? |
| c) Co-ordinate support for learners to enable them to fulfil their potential. | CL & D Plan target – ongoing | Add NHI, Disability Partnership |
| d) Improve capacity in communities to engage with public agencies | Roll out of standards of community engagement | Add Disability Partnership |

###### Priority Area 2 - Encouraging Lifelong Learning and Developing Community Capacity

###### AIM 3 – Highland having the infrastructure to keep it at the forefront of modern rural regions

| What are we going to do | What Progress Has Been Made? | What Changes Are Required? |
| --- | --- | --- |
| a) Support the further development of UHI. | TDAT NHC extending undergraduate and post graduate courses | Achieve 2008 |
| b) Support to vulnerable families with children aged 0-3 : |  | Add THC – Surestart Clarify output |
| c) Promote the concept of “learning” as a major sector of the economy. | NHC Audit | Needs to identify Caithness as separate area? Who would use this information Add community based initiatives |
| d) Continue the development of New Community Schools approaches. |  | Needs clarification |

Priority Area 3 - Improving Health and Wellbeing

AIM 1 = More pepople chooisng to live, work and learn in highland – and able to do so

| What are we going to do | What progress has been made? | Any changes needed? |
| --- | --- | --- |
| a) Develop appropriate services to support and promote positive parenting. | Report prepared by Miles Greenford on Positive Parenting – presented to North Community Health Partnership |  |
| b) Jointly promote opportunities for increased physical activity for children and young people. | Highland Council and Sports Council are agreed as key partners. Partnerships for Wellbeing (Director: George Bruce) should be added. Community schools being developed will provide more facilities and Halkirk Football Academy. Although there are gaps in funding. Thurso Harbour Sports facilities Centre for “Sea Activities” has begun development. | Consider adding Partnership for Wellbeing to key partners list. |
| c) Jointly address stigma and discrimination and promote the benefits of diverse communities. | Integration of people suffering from mental health into the community. Funding prepared for in-migrant and elderly groups to be helped to integrate into the wider communities. Caithness Deaf Care aims to address this also. | Qualify the focus and remove the wording “stigma” Change to jointly address discrimination (real and perceived) |

Priority Area 3 – IMPROVING HEALTH AND WELLBING

AIM 2 = Individuals and communities feel they are dealt with equitably

| What are we going to do | What progress has been made? | Any changes needed? |
| --- | --- | --- |
| a) Work together to focus community development activity in areas of need. | Health Improvement Group have met who comprise of health related voluntary groups in the community and are focussing on areas of need in the community. | Add NDA to list of key partners. |
| b) Reduce financial exclusion and fuel poverty. | “Establish a credit union” - DEFER, should be added -> | Change “fuel poverty strategy” for Caithness to include “Energy Poverty Strategy”. Promotion of what is available. A one method does not suit the individual’s needs. Promote local. |
| c) Improve the health of carers | Unaware of progress of 3 year milestone | Crossroads should be included in the “Key Partners” list. |
| d) Address issues relating to access to healthy food. |  | Remove Health & Happiness and Shirley Project from the key partners albeit they work with other key partners in this process. Local Health Service Partnership should be changed to Community Health Partnership. Add – Crofters Commission and Hi Food Link. |

###### Priority Area 3 – IMPROVING HEALTH AND WELLBING

###### AIM 3 – Highland having the infrastructure to keep it at the forefront of modern rural regions

| What are we going to do | What progress has been made? | Any changes needed? |
| --- | --- | --- |
| a) Ensure Highland Wellbeing Alliance agencies become health improving organisations and promote healthy public policy. | Health Improvement Network has been established. | Key Partners: New Strategic Working Group on sensory issues chaired by A Macdonald should be listed. (relating to blindness and deafness). Under key partners add “Community health partnership” |
| b) Jointly develop a strategy for using the media more effectively to promote health and health improvement. | Key Partners Community Health Partnership have been doing a lot of work on this. | S.P.O.C. should be Community Health Partnership (CHP)? Annual report on progress of CHP & Caithness Partnership for ease of circulation for elderly, vulnerable groups as they may not have internet access. Inclusion of S.H.A.W. (SCOTTISH HEALTH AT WORK) to raise awareness. |
| c) Promote ‘Scotland’s Health at Work’ across public, private and voluntary sector agencies. |  |  |

| What are we going to do | What progress has been made? | Any changes needed? |
| --- | --- | --- |
| a) Via the Housing Strategy and Housing Strategy Partnership Group, agree investment priorities and support projects through joint or coordinated funding. | Priorities are agreed and developments are proceeding | Difficulties anticipated with Scottish Water |
| b) Develop strategic “land banks” of effective/development-ready land for housing, particularly for affordable housing. | Land has been identified. Work in progress. | Note Renewable Energy Aspect |
| c) Joint work to identify all the demands which may face the construction industry in Highland in the coming years so as to avoid constraints on development. | Highland Housing Alliance Pilot Scheme for SIP Panel Project | Scottish Water |
| d) Adopt and promote new planning guidance on sustainable development in the housing sector. |  | Priority for Housing Development Forum |

PRIORITY AREA 4 - INVESTING IN HOUSING AND ITS INFRASTRUCTURE

AIM 2 = Individuals and communities feel they are dealt with equitably

| What are we going to do | What progress has been made? | Any changes needed? |
| --- | --- | --- |
| a) Assist people to live independently by co-ordinating support and prevention services. | Discussions with Social Work Department on needs and budget priorities | Like to see Social Work as key players |
| b) Help communities understand and accept the reasons for the requirement for more housing | Open days at IatE plus planning consultation meetings. |  |

PRIORITY AREA 4 - INVESTING IN HOUSING AND ITS INFRASTRUCTURE

###### AIM 3 – Highland having the infrastructure to keep it at the forefront of modern rural regions

| What are we going to do | What Progress Has Been Made? | Any Changes Needed? |
| --- | --- | --- |
| a) Work to ensure that the priorities and resources for water and sewerage infrastructure investment programmes take account of the need to create more effective land for housing across Highland. | Refer to 1a. and 1c. |  |
| b) Support innovative affordable and fit for purpose solutions to the provision of essential infrastructure for housing in rural areas. | Land banks established for Pulteneytown, Initative at the Edge and Castletown | Develop Land bank for Dunnet |
| c) Build on the success of Local Housing Development Forums, as a means of addressing complex local issues and identifying practical solutions to problems. |  | Part of Socio Economic Agenda (Dounreay) Possible link to North Highland Initiative |
| d) Assemble information from all Highland Wellbeing Alliance partners and co-operating agencies on their land holdings in Highland. |  | Led at Highland level |
| e) | Cancelled |  |
| f) |  | Extend 3 year milestone to include other essential services. |
| g) | Initative At the Edge surveys Survey of Tannach community council area. Programme to be rolled out through Forums – as 3 year milestone. -> |  |

###### Priority Area 5 - Improving Transport

###### AIM 1- More people choosing to live, work and learn in highland – and able to do so

| What are we going to do | What Progress Has Been Made? | Any Changes Needed? |
| --- | --- | --- |
|  | Setting up CTF to liaise with HITRANS Production of CT Vision 2006 Good links with other bodies and authorities Lobbying work (Minister, MSP, MP) |  |
| a) Working with HITRANS to lobby for improvements to external transport links to the Highlands | ROAD Lobbying/commitment to updating costings and design for Berriedale A836 out to tender 2nd Phase Ord of Caithness Plan published AIR Air link to Orkney restored Air Discount Scheme RAIL Study on Dornoch Rail Link Funded and underway North Line identified as nationally significant? SEA Faroese link to Scrabster June 2007 Cruise ships marketing ongoing and liaison with tourism bodies. Wick Harbour initiative – new marina going ahead | Caithness Focus Replaced to match the Vision Maintain and expand air services to suit demand Need to get Shetland air link restored Stimulate public/business use of air services Redefine benefit of ADS Air link to Inverness at appropriate times. Promote positive impact of having a railway line. Developments of rail heads. Marketing of Caithness as a shopping destination from Orkney |
| b) Working with transport operators to improve internal transport systems within the Highlands | CTF set up and working on timetabling (Tesco buses running) |  |
| c) Improve the environment for pedestrians and cyclists in City and Town centres and assist economic development. | Parking for bikes at new developments 20 mph zones at schools across Caithness and pedestrian crossings Signposting done in Thurso (Town centre) |  |
| d) Improve the environment for pedestrians and cyclists in rural areas. |  |  |

Priority Area 5 - Improving Transport

AIM 2 = Individuals and communities feel they are dealt with equitably

| What are we going to do | What progress has been made? | Any changes Needed? |
| --- | --- | --- |
| a) Working with the community to improve access to the spectrum of public transport. | No progress yet | Transport Forum should be working on this. |
| b) Working with HITRANS to improve the uptake of concessionary fare travel. |  | Transport Forum should be working on this |
| c) Working with the Scottish Executive to improve the safety in the transport environment around schools | Traffic calming – Crescent Street, Halkirk, completed – 20mph round schools | Extend to all schools in 2007. |

Priority Area 5 - Improving Transport

###### AIM 3 – Highland having the infrastructure to keep it at the forefront of modern rural regions

| What are we going to do | What progress has been made? | Any changes needed? |
| --- | --- | --- |
| a) Working with HITRANS and the Scottish Executive to increase investment in Transport infrastructure, both revenue and capital |  |  |
| b) Working with the Northern Constabulary and the Scottish Executive to make the road network in the Highlands safer for the travelling public. | AIP scheme at Westfield WMS – Safe routes to Watten Safe routes to school – being worked on | Add “and villages” after towns. |
| c) Working with the Health Board and communities to provide innovative rural public transport to meet the social need in rural areas for improved access to essential services, to encourage sustainable rural communities | Dunbeath Community Transport |  |
| d) Working with freight operators to improve the freight transport network. |  |  |
| e) Working with public and private sector bodies to encourage the use of green travel plans. | ‘Lift share’ pilot agreed with HITRANS Realistic and competitive fuel prices | Reword fuel aim |

PRIORITY AREA 6 - Enhancing Cultures, HERITAGE, the gaelic language and the Natural Environment

###### AIM 1- More people choosing to live, work and learn in highland – and able to do so

| What are we going to do | What progress has been made? | Any changes required? |
| --- | --- | --- |
|  | Raised awareness of the LBAP | MORE - Us reporting to our agencies - Caithness Partnership Wider communities/non rep. groups Quarterly contact both ways Sub Group meetings once a quarter Can bring in extra members |
| a) A programme of local biodiversity action and awareness raising initiated by local community groups, supported by Caithness Partnership. | Project funding through Highland Biodiversity Partnership Biodiversity Group branched out build networks to help forward plan Feeling of competition Achavanich Plans for Website Communication with other areas in subgroup -> (Caithness Partnership Website) | Continue Communication A start – continue Move forward including Archaeology Arts |
| b) Implement the Highland Waste Strategy. Work in Partnership with Community Groups and Not for Profit Sector to divert household waste from landfill by reuse, refurbishment and recycling projects. | College based Talk Domestic Moving Forward Thurso & Wick Recycling Centres Not enough | Continue Take up and run Commercial New Sub Group – SEPA, COLLEGE, COUNCIL, UKAEA |
| c) Public spaces including parks and road corridors managed to benefit biodiversity. | Nothing Talk | Action |
| d) Promote access to the natural environment for sustainable activity. | Public Access Forum 1 Meeting Access for surfers in Thurso | Continue Being moved forward |
| e) Encourage parents to raise their children as Gaelic speakers. | Gaelic - Status Quo | ? |
| f) Provide Gaelic medium education and offer Gaelic as a second language in primary and secondary schools. |  |  |
| g) Provide opportunities and support for adults wishing to learn Gaelic | Blas Festival More successful | More successful |
| h) Continue, develop and increase the range of arts, music and heritage related events linked to Gaelic that take place across the Highlands, for example, ensure Gaelic activities are at the heart of the 2007 Scottish Year of Highland Culture | Same as above | Same as above |
| i)New Sub Section - Archaeology | C.A.T. Rof S Sustainability conference Teaching purely Arts 2 x conference – SAM/HAF etc | Continue to develop to further permanency -> other subsequent areas aware of model |
|  | Cost Biological Records Centre | Build up resources |

PRIORITY AREA 6 - Enhancing Cultures, HERITAGE, the gaelic language and the Natural Environment

AIM 2 = Individuals and communities feel they are dealt with equitably

| What are we going to do | What progress has been made? | Any changes needed? |
| --- | --- | --- |
| a) Deliver a year when Scotland celebrates Highland culture. |  |  |
| b) A renewed Biological Records Centre will be established |  |  |
| c) Support and promote Gaelic as a community language |  |  |
| d) New subsection – local dialects |  |  |

PRIORITY AREA 6 - Enhancing Cultures, HERITAGE, the gaelic language and the Natural Environment

###### AIM 3 – Highland having the infrastructure to keep it at the forefront of modern rural regions

| What are we going to do |  |  |
| --- | --- | --- |
| a) Strategic Environmental Assessment (SEA) of all significant plans. |  |  |
| b) Core Path Networks identified around all major settlements in consultation with local communities. |  |  |
| c) Highland Shellfish Management Organisation will manage the Highland Regulating Order through the involvement of local advisory groups. |  |  |
| d) A new international traditional music festival to be established |  |  |
| e) A new Highland archive centre to be built as part of the Highland Centre and Area Archive Strategy. |  |  |
| f) Continuing Professional Development for teachers to include Gaelic language, heritage, culture and environment. |  |  |
| g) Develop a youth information service (HLYS) to encourage participation in community based themed activities. |  |  |

Priority Area 7 – Developing safe, strong and attractive communities

###### AIM 1- More people choosing to live, work and learn in highland – and able to do so

| What are we going to do | What progress has been made? | Any changes needed? |
| --- | --- | --- |
| Develop an Antisocial Behaviour Strategy. | Strategy in place Warden Services in Pulteney – extended to 2008 – SE funding Wick CCTV ASB Officer – half post increased to 23 hours | Include Wick CCTV Need more!! |
| b) Support the activities of the HIFB Community Safety Strategy | Home Fire Risk Assessments ongoing H.I.F.R.S. Website links expanded Partnership with NH College in a learning for life course Fire Cadet Scheme started in Wick | Include Environmental Scanning Report and recommendations for Pulteneytown which need to be progressed |
| c) Develop opportunities for intergenerational work. | Constant review of diversionary activities by individuals | Include Fire Cadet Scheme Other groups etc Lunch clubs/after school clubs Possibly a need for an action for the CSA Group to progress. |
| d) Encourage communities to take up the concept of Home Zones | Homezone (mini) being considered for Pulteney PPP have progressed other community projects |  |
| e) Develop a strategy for working with the media to improve community safety and perceptions of crime levels. | Media Links by individual agencies | CSAG need to look at how it liaises with projects |
| f) Develop a positive view of risk. | Home Safety Assessments CCTV Operation values | Include all in Plan |
| g) Encourage safe behaviours by visitors to the Highlands. | Leaflets circulated regularly by all relevant agencies etc |  |
| h) Develop an education campaign to raise awareness and reduce incidents of driving under the influence of drugs and alcohol. | Educate public re drink/drug driving to reduce number | Include the drug driving aspect |
| i) Implement the HDAAT Corporate Action Plan. | CDAF continue to progress actions pertinent to Caithness |  |

Priority Area 7 – Developing safe, strong and attractive communities

AIM 2 = Individuals and communities feel they are dealt with equitably

| What are we going to do | What progress has been made? | Any changes needed? |
| --- | --- | --- |
| a) Develop a Highland Wellbeing Alliance Equal Opportunities and Diversity Strategy. | Interpreters service High level discussions ongoing |  |

Priority Area 7 – Developing safe, strong and attractive communities

###### AIM 3 – Highland having the infrastructure to keep it at the forefront of modern rural regions

| What are we going to do | What progress has been made? | Any changes Needed? |
| --- | --- | --- |
| a) Explore potential for sharing of policing and emergency service resources (including staff and facilities) | This needs to be removed as it is not an aspiration of any of the agencies at executive level at this time | Remove |
| b) Promote both formal and informal play opportunities | Lots of youth and voluntary work/clubs etc All weather pitch Wick Upgrade to all weather pitch Thurso Rosebank Playing Fields upgrade in partnership with UKAEA SE Caithness continues development group |  |
| c) Build community capacity | Plan in place but has yet to be progressed in much of its content. |  |

# Text boxes

PRIORITY AREA 4 - INVESTING IN HOUSING AND ITS INFRASTRUCTURE

###### AIM 1- More people choosing to live, work and learn in highland – and able to do so